## Plan
Project Name | Hack Zika 2017
Project Manager | Mike Turtora
Action | Responsible | Priority | Status | Start Date | End Date | Notes
Goal A: Kiosk Game
1. Identify SOW author (Andrea Washaven?) and begin dialogue to define the challenge (target audience and information to include) (6/26/17) |  |  |  |  | 2017-06-26
2. Assign challenge champion (subject matter expert available at event) (7/21/17) |  |  |  |  | 2017-07-21
3. Ron mentioned the possibility of a badge or certificate of some sort for residents (Mosquito Hawk). This could be awarded to game “winners” or could be part of Digital Inspector
4. Need specs for library kiosks
5. Specify (finalize?) information requirements to include (7/14/17) |  |  |  |  | 2017-07-14
6. Identify other resources (7/14/17) |  |  |  |  | 2017-07-14
7. Write challenge description (8/1/17) |  |  |  |  | 2017-08-01
8. Upload challenge package to web (hackathon github repository) (8/31/17) |  |  |  |  | 2017-08-31
9. Define judging criteria (8/31/17)
Create Judging sheet
Create fun name for objective
Goal B: Digital Inspector
1. Inspection form or ideas for checklist (6/30/17) |  |  |  |  | 2017-06-30 | If no form, interview inspector or shadow during an inspection? Take photos? (7/14/17)
2. Identify other resources (7/14/17) |  |  |  |  | 2017-07-14
3. Specify app platforms (desktop or mobile or both: mobile preferred?) (7/14/17) |  |  |  |  | 2017-07-14
4. Assign challenge champion (subject matter expert available at event: an inspector?) (7/21/17) |  |  |  |  | 2017-07-21
5. Write challenge description (8/14/17) |  |  |  |  | 2017-08-14
6. Upload challenge package to web (hackathon github repository) (8/31/17) |  |  |  |  | 2017-08-31
7. Define judging criteria (8/31/17) |  |  |  |  | 2017-08-31
Create Judging sheet
Create fun name for objective
Goal C: Spray Truck Routing (Turn By Turn Navigation)
Specify wind directions (6/30/17) |  |  |  |  | 2017-06-30
Identify other resources (7/14/17) |  |  |  |  | 2017-07-14 | Historical truck route data, if it exists
Obtain GIS layers (7/21/17) |  |  |  |  | 2017-07-21
Specify app platforms (desktop or mobile or both) (7/14/17) |  |  |  |  | 2017-07-14
Assign challenge champion (subject matter expert available at event: a driver?) (7/21/17) |  |  |  |  | 2017-07-21
Write challenge description (8/14/17) |  |  |  |  | 2017-08-14
Upload challenge package to web (hackathon github repository) (8/31/17) |  |  |  |  | 2017-08-31
Define judging criteria (8/31/17) |  |  |  |  | 2017-08-31
Create Judging sheet
Create fun name for objective
Goal D: Zone Picker (Prescriptive Analytics)
Goal #: Food for event day
Goal #: Event Swag
Goal #: Event Day Set-up
Goal #: Sponsorship/ Funding
Goal #: Website
up-date content to reflect Hack Zika 2017 | Jessica |  |  | 2017-06-23
Goal #: Objective prizes

## Sample
Project Name | Event ABC
Project Manager | Anthony G.
Action | Responsible | Priority | Status | Start Date | End Date | Notes
Goal #1: Select Venue
Identify venue options | Sally J. | High | Complete | 2017-09-30 | 2017-10-02
Visit venues | Sally J. | High | Complete | 2017-10-05 | 2017-10-09 | Must send contracts by 10/10
Sign contract | Maria S. | High | Complete | 2017-10-12 | 2017-10-12
Goal #2: Secure Speakers
Recruit speakers | Sally J. | High | In progress | 2017-10-07 | 2017-10-12
Speaker bios | Sally J. | Medium | Not started | 2017-10-12 | 2017-10-14
Create and send speaker packets | Maria S. | Medium | Not started | 2017-10-13 | 2017-10-16 | Send to stakeholders
Confirm speakers | Sally J. | High | Not started | 2017-10-17 | 2017-10-18
Goal #3: Recruit Sponsors
Identify sponsors | John S. | High | In progress | 2017-10-13 | 2017-10-19
Write up sponsor agreement | Maria S. | Medium | Not started | 2017-10-15 | 2017-10-16
Send emails | John S. | High | In progress | 2017-10-19 | 2017-10-21
Make cold calls | John S. | Medium | Not started | 2017-10-21 | 2017-10-23 | From sales team
Goal #4: Promote event
Create banners | Morgan K. | Low | Not started | 2017-10-26 | 2017-10-28
Order swag | Morgan K. | Low | Not started | 2017-10-28 | 2017-10-28 | Coffee mugs, totes, pencils
Create social media strategy | Corrine J. | Low | In progress | 2017-10-13 | 2017-10-26
Make marketing materials | Karen Z. | High | Not started | 2017-10-26 | 2017-10-30
Or, Click Here to Create Your Action Plan in Smartsheet