## AIR
Code for Hillsborough
Item | Contact | Completed | Status | Notes | Time
Participant list
Invite list
Save the Date + Digital Invite
National site
Registration site
Press Release for event
Press Release for media preview
Courtesy Email to participants and speakers
Email reminder
Food ordered
Social Media
Organize Data sets
Posters and Stickers
Flyers
Name tags
Sign-in
Media packets
Event signs
PowerPoint
Supplies
Tables
Judging Criteria
Screen
Projector
Portable White Board
Trash cans
Trash bags
Easels
RSVPs
Promotional items
Prizes
Friday, June 5
Event signs
PowerPoint
Social at Event
Snacks + Water + Soda
Sign-in
Saturday, June 6
Breakfast and Coffee
Nametags
Sign-in
Social at Event
Snacks + Water + Soda
Sunday, June 7
Breakfast and Coffee
Nametags
Sign-in
Social at Event
Food + Snacks + Water + Soda

## Itinerary
Thursday, June 4 @ 2 p.m. - Media Preview
Time | Task | Who | Notes
Noon | Arrive for set up | Jennifer, Terri, Kyle, Doug D., John | Jennifer create ppt + Terri provide slide deck
| Code for Tampa Bay Refreshments | Terri | Terri pick up from Wright's Gourmet (mixed sandwich tray, mixed cookie tray, bottled water, tea, plates, cups, napkins)
12:30 p.m. | HTV Arrive for set up | Crystal + Comm. Team | Crystal arrange with HTV podium sign and AV and Steve for event signage to include: street and parking garage
| Banner | Crystal + Jennifer | Jennifer bring banner
2 p.m. | Sign-in | Microsoft | Jennifer printed sign-ins, nametags
| PPT running in a loop | Jennifer | Jennifer's ppt
| Social Media |  | Social Media posting
2:30 p.m. | Lindsey Kimball | Lindsey | Crystal provide Podium Agenda
| John Punzak, Captain | John | Have bio
| Terri Willingham, Captain | Terri | Have bio
| Mark Sharpe, TIA | Lindsey | Lindsey invite + Crystal provide Podium Agenda
| Commissioner Murman | Lindsey | Lindsey invite + Crystal provide Podium Agenda
3 p.m. | Laicos Update Reveal (web version) | Kyle Matthews | Kyle submitted desc. + site to Crystal
3:30 p.m. | Networking + Registration for Weekend | Jennifer, Terri, Kyle, Doug D., John
Friday, June 5 @ 4 p.m. - Meet + Greet and Projects and Data Sets Reveal
Time | Task | Who | Notes
Noon | Setup on Friday for Weekend | Jennifer, Terri, Kyle, Doug D., John | Jennifer bring tables, covers, supplies
3 p.m. | Code for Tampa Bay Meet + Greet Appetizers arrive | Terri | Terri pick up from Wright's Gourmet (mixed sandwich tray, mixed cookie tray, bottled water, tea, plates, cups, napkins)
4 p.m. | Sign-in | Microsoft | Jennifer printed sign-ins, name tags
| PPT running in a loop | Jennifer | Jennifer's ppt
Networking
4:30 p.m. | Projects and Data Sets Reveal | John | John provide overview
5:30 p.m. | Absolute Mobile Solutions After-party | Alfred | Terri coordinating
Saturday, June 6 @ 9:30 a.m. - 11 p.m. - Code for Hillsborough
Time | Task | Who | Notes
9 a.m. | Arrive | Team
9:30 a.m. | Registration | Jennifer | Jennifer register
| Project Sign-up | Terri | Terri and white board sign-up
9:45 a.m. | The Grind Breakfast + Coffee | John | John coordinating - breakfast and coffee arrive at 9 a.m.
| Welcome: Joe Healy, Microsoft | Joe | Topic: Welcome
| Breakfast speaker: John Punzak, Red Hat | John | Topic: Opening on Civic Hacking
10 a.m. | Coding Event
Noon | TekBank Lunch - Grimaldi's Pizza | Sid Hassan | Terri coordinating with Sid
| Lunch Speaker: Sid Hassan, TekBank | Sid bringing the lunch | Topic: Professional Services in The New Paradigm of Compute, Networking & Storage - 15 min.
4 p.m. | Afternoon Speaker - Priya, CoderDojo |  | Topic: Coding for Laughs Is No Laughing Matter - 10 min.
| Code for Tampa Bay Snacks | Terri
6 p.m. | Forex Factory Dinner - Miguel's | Doug, Terri
| Dinner Speaker: Alfred Goldberg, Absolute Mobile Solutions |  | Topic: 3 P’s of Mobile Engagement - 20 min.
8:30 p.m. | End of Day Wrap-up | John and Terri
9 p.m. | Absolute Mobile Solutions | Alfred | Terri coordinating
Sunday, June 7 @ 9:30 a.m. - 5 p.m. - Code for Hillsborough
Time | Task | Who | Notes
9:30 a.m. | Registration | Jennifer | Jennifer register
| Project Sign-up | Steve | Steve and white board sign-up
| McDonald's Breakfast | Doug | Doug coordinating
| Kahwa Coffee | Jennifer | Jennifer coordinating
10 a.m. | Coding Event
Noon | The Iron Yard Lunch - Jimbos BBQ | Toni Aliberti
| Lunch Speaker: Ryan Dorrell, AgileThought |  | Topic: The Path to Professional Software Developer
| Code for Tampa Bay Snacks | Terri
3 p.m. | Presentations | Mark Sharpe open | PRIZES - Tampa Innovation Alliance
| Judges: Sid Hassan, TekBank; Mike Cook, GuidePoint Security; Ryan Negri, Laicos; Toni Aliberti, The Iron Yard; Steve Willingham, Eureka! Factory |  | 1st, 2nd, 3rd place, and People's Choice prizes

## De-Brief
De-Brief Notes
Create judge packets and review/ train judges a day prior to judging
Send out Feedback survey to attendees
Have Registration outside org.
Focus on using national website
Have Promotions video sooner to promote event
Have a Coding track and Concept track
Have a visual demo on presenting and workshop
Test laptops before presentations
Great location
Have a Microsoft Challenge or Host Challenge
Simplify food - one main food vendor
Food partners take care of their own food
Partner package - marketing
Take leftover food to shelter
Have an extra kids room or break room